## Sheet1
1. Fielding dismissals nhi dikh rha |  | Done | will reflect after sync data
2. Runs, Matches, Wickets 725.0, 46.0 format me aa raha hai. Integer stats me decimal nahi hona chahiye. price / eco / avg / strike rate me decimal makes sense |  | Done | reflecting
3. Match dikh rha hai but innings nhi. both should be there |  | Done | reflecting
4. subhashis das ka photo nhi aaya , abhik ganguly and few others ka bhi. sayd photo rendering me issue hoga kuch |  | Done | reflecting
5. When saving surprise player or prediction - taking too much time. may be my system is slow and 4 tabs khula tha but check once |  | not in scope
6. ek deadlock error bich bich me aa rha hai. some red code |  | Done | will work post deployment
7. after every action probably all captains and admins need to refresh the page |  | not in scope
8. While last bid joker me RTM trigger is not working but same is working in force nomination |  | Done | will work post deployment
9. During spin wheel it takes some time to present the spin effect or putting the player on block. sab alag alag devide se dekhega to sayd dikhe |  | not in scope
10. surprise player purchase ke baad purse update ho rha hai correctly but screen pe koi popup ya message nhi aaya |  | done | reflecting
11. Penalty ke case me bhi koi on-screen message ya dedicated tab nhi hai. while there is a suprise player tab for admin jahan surprise player dikhta hai . prediction wala tab nhi . kyun ki bad me koi player ka prediction correct nikla aur phir bhi system nhi trigger kia to audit ke lie kuch base nhi rhega . so uska bhi ek hona chayie |  | done | reflecting
12. After each player sold interface takes us to first tab - manage teams |  | not in scope
13. marquee nomination can be seen by everyone. no secrecy right? |  | done | reflecting
14. Pre auction me lock krne ka option 8 se km player ke penalty . saprediction me bhi aa rha ha i. so auctioneer ko puchkr confirm krna hoga ki sabne 2-2 prediction kia ya nhi. |  | need to check with admin once more
15. Minimum purse data is not as per dynamic rule |  | Done | will work post deployment
16. Surprise bonus rule me ek concern hai: |  | Done | reflecting
* 10% of base price or 25 lakh whichever is higher
* lets say impact player 20 lakh me kharida aur surprise nikla
* 10% = 2 lakh but 25 lakh bonus milega
* bonus player ke base price se bhi zyada ho jayega
17. Penalty rule me bhi same concern: |  | Done | reflecting
* Penalty should never be more than player base price
* aur agar penalty lagne ke baad total bid > max bid available ho jaye then player milna hi nhi chahiye kyunki minimum reserve maintain krna mandatory hai
* so penalty must need to be restricted to max bid available
18. Koi player glti se kisi aur ke name pe sold ho gya to undo kaise krenge? Need some undo/reversal option. |  | Done | reflecting